|  |  |
| --- | --- |
| Project name:  brillianCRM | Work package title:  Training |
| Work package description:  For the end user as well as for the key user it is really important to be able to work on the new system. Therefore, training has to be performed. Depending on the difficulty of the new software the training can last a few days | |
| Aim of work package:  Train end users and key users to use the software adequately | |
| Predecessor:  Software Development | Successor:  Project Approval |
| Duration:  12 days | Effort in man days (MD):  180 MD |
| Responsible person(s):  13 Consultants, Project Manager, Assistant | |
| Additional information: | |