## 1 Phase
[8 empty] | Assistent | PM | Consultant | IT Spec.
[8 empty] | 600 | 1200 | 900 | 900
[8 empty] | 1 | 1 | 13 | 5
Time | Project Initiationsphase | Resources | Days | Price per Day | Sum | RESULT = 94 200€
2 Month | Project charter | PM | PM (66 days) | x 1200€
| Functional Requirements | PM | Assistant (25 days) | x 600€ | =
| Staffing | PM
| Stakeholderanalysis | PM + Assistant | Please choose the correct amount of euro. |  |  |  |  | 79200
| Risk analysis | PM + Assistant | [5 empty] | 15000
| Milestone Planning | PM + Assistant | [5 empty] | 94200
| Resource allocation | PM + Assistant
| Budget Planning | PM + Assistant
104 600€ |  |  | 84 400€ |  |  |  | 94 200€

## 2 Phase
[8 empty] | Assistent | PM | Consultant | IT Spec.
Time | Project Planning | Resources | Days | Price per Day | Sum |  |  | 600 | 1200 | 900 | 900
3 Month | Kick-Off Meeting | Everyone | PM (37 days) | x 1200€ |  | RESULT = 792 300 € |  | 1 | 1 | 13 | 5
| Identify Work packages | PM + Assistant | Assistant (33 days) | x 600€
| Create work breakdown structure | PM + Assistant | Consultans (568 days) | x 900€
| Detailed Time Planning/ Milestone Planning | PM + Assistant | IT Specialists (241 days) | x 900€ | =
| Determination mobile devices | Assistant
| Change Management | PM + Consultants | Please choose the correct amount of euro. |  |  |  | 44400
19800
| Actual State Analysis | [5 empty] | 511200
| Customer Analysis | Consultants |  |  |  |  | 216900
| Sales force analysis | Consultants |  |  |  |  | 792300
| Process Analysis | Consultants + IT Specialists
| Data Analysis | Consultants + IT Specialists |  |  |  |  | 7032
Target State Analysis
| Design Customer Relationship Strategy | Consultants
| Prozess adaption | Consultants + IT Specialists
| Data model Creation | Consultants + IT Specialists
| Creation of Migrationconcept | Consultants + IT Specialists
| Requirements Specification | Consultants
| Customizing | IT Specialists
| 973 200€ | 792 300€ | 104 600€

## 3-4 Phase
Time | Project Executionphase | Resources | Days | Price per Day | Sum
3 Month | Development in India | IT Specialist | PM (35 days) | x 1200€ |  |  | 42000
| Data Migration | Consultants + IT Specialists | Assistant (65 days) | x 600€ |  |  | 39000
| Pilot running | Consultants + IT Specialists | Consultants (432 days) | x 900€ |  |  | 388800
| Implementation (testing environment) |  | IT Specialists (169 days) | x 900€ |  |  | 152100
| Testing |  |  |  | 639900 |  | 621900
| Implementation (live system) | IT Specialists
| Training | Consultants |  |  |  |  | 5608
| Rollout of the CRM System | Consultants + It Specialist
Time | Project Closingphase
1 Month | Approval | PM + Assistant | PM (20 days) | x 1200€ |  |  |  | 24000
| Leassons learned | All Teammembers | Assitant (20 days) | x 600€ |  | RESULT 270.000 € |  | 12000
|  |  | Consultants (180 days) | x 900€ |  |  |  | 162000
|  |  | IT Specialists (80 days) | x 900€ |  |  |  | 72000
[5 empty] | = |  |  | 270000
| 270 000€ | 312 500€ | 267 400€
| 1 778 400€ |  | 1 | 94200
|  |  | 2 | 792300
|  |  | 3 | 621900
|  |  | 4 | 270000
1778400