## 1 Phase
[8 empty] | Assistent | PM | Consultant | IT Spec.
[8 empty] | 600 | 1200 | 900 | 900
[8 empty] | 1 | 1 | 13 | 5
Time | Project Initiationsphase | Resources | Days | Price per Day | Sum | RESULT = 60 000€
2 Month | Project charter | PM | PM 40 | x 1200€ | 48000
| Functional Requirements | PM | Assistant 20 | x 600€ | 12000
| Staffing | PM |  |  | 60000
| Stakeholderanalysis | PM + Assistant | Please choose the correct amount of euro.
| Risk analysis | PM + Assistant
| Milestone Planning | PM + Assistant
| Resource allocation | PM + Assistant
| Budget Planning | PM + Assistant
80 000€ |  |  | 40 000€ |  |  |  | 60 000€

## 2 Phase
[7 empty] | Assistent | PM | Consultant | IT Spec.
Time | Project Planning | Resources | Days | Price per Day | Sum |  | 600 | 1200 | 900 | 900
3 Month | Kick-Off Meeting | Everyone | PM 60 | x 1200€ | 72000 | RESULT = 10 620 000€ | 1 | 1 | 13 | 5
| Identify Work packages | PM + Assistant | Assistant 30 | x 600€ | 18000
| Create work breakdown structure | PM + Assistant | 13 Consultans 60 (780) | x 900€ | 702000
| Detailed Time Planning/ Milestone Planning | PM + Assistant | 5 IT Specialists 60 (300) | x 900€ | 270000
| Determination mobile devices | Assistant |  |  | 1062000
| Change Management | PM + 13 Consultants | Please choose the correct amount of euro.
Actual State Analysis
| Customer Analysis | 3 Consultants
| Sales force analysis | 3 Consultants
| Process Analysis | 3 Consultants + 3 IT Specialists
| Data Analysis | 4 Consultants + 2 IT Specialists
Target State Analysis
| Design Customer Relationship Strategy | 4 Consultants
| Prozess adaption | 3 Consultants + 1 IT Specialists
| Data model Creation | 4 Consultants + 2 IT Specialists
| Creation of Migrationconcept | 2 Consultants + 2 IT Specialists
| Requirements Specification | 13 Consultants
| Customizing | 5 IT Specialists
| 10 000 000€ | 10 620 000€ | 10 144 000€

## 3-4 Phase
Time | Project Executionphase | Resources | Days | Price per Day | Sum
3 Month | Development in India | 1 IT Specialist | PM 60 | x 1200€ | 72000
| Data Migration | 1 Consultants + 2 IT Specialists | Assistant 30 | x 600€ | 18000
| Pilot running | 5 Consultants + 2 IT Specialists | Consultants 60 (780 days) | x 900€ | 702000
| Implementation (testing environment) |  | IT Specialists 60 (300 days) | x 900€ | 270000
| Testing |  |  |  | 1062000
| Implementation (live system) | 3 IT Specialists |  |  | 1062000
| Training | 3 Consultants
| Rollout of the CRM System | 8 Consultants + 2 It Specialist
Time | Project Closingphase | [6 empty] | 354000
1 Month | Approval | PM + Assistant | PM 20 | x 1200€
| Leassons learned | all | Assitant 10 | x 600€ |  | RESULT 324000
|  |  | Consultants - IT Specialists (360) | x 900€
=
| 324 000€ | 402 500€ | 297 400€
12096000
2538000
21 624 000€