## Phase 1
Initiationphase
Duration: 2 Months
Project Initiation | Resources |  | days | Cost of initiation:
Project charter | Project manager |  | 5 |  | Duration in days | Cost per day | Cost per Ressource
requirement specification | Project manager |  | 8 | Project manager | 40 | 1200 | 48000
Staffing | Project manager |  | 7 | Assistant | 20 | 600 | 12000
Stakeholderanalysis | Project manager | Assistant | 3 | Consultants | - | 900
Risk analysis | Project manager | Assistant | 4 | IT Specialists | - | 900
Milestone Planning | Project manager | Assistant | 4
Resource allocation | Project manager | Assistant | 4
Budget Planning | Project manager | Assistant | 5 |  |  | total cost: | 60000
40
Cost of ressource per day:
| Project manager | 1200
| Assistant | 600
| Consultants | 900
| IT Specialists | 900

## Phase 2
Planning |  | con | it | Duration of Task | Assistant | PM | Consultants | IT-specialists | Consultant-days | it-specialist-days
Project Planning | Resources | [9 empty] | Cost ofplanning:
Kick-Off Meeting | Everyone |  |  | 2 |  | 2 | 13 | 5 | 26 | 10 |  | workdays in period | Price per day | total cost
Identify Work packages | PM + Assistant |  |  | 3 |  | 3 | 13 | 5 | 39 | 15 | Project manager | 60 | 1200 | 72000
Create work breakdown structure | PM + Assistant |  |  | 6 |  | 6 | 13 | 5 | 78 | 30 | Assistant | 30 | 600 | 18000
Detailed Time Planning/ Milestone Planning | PM + Assistant |  |  | 2 |  | 2 | 13 | 5 | 26 | 10 | Consultants | 780 | 900 | 702000
Determination mobile devices | Assistant |  |  | 2 |  | 2 | 13 | 5 | 26 | 10 | IT Specialists | 300 | 900 | 270000
Change Management | PM + 13 Consultants | 13 |  | 3 |  | 3 | 13 | 5 | 39 | 15
[6 empty] | 0 | 13 | 5 | 0 | 0
Actual State Analysis | [5 empty] | 0 | 13 | 5 | 0 | 0
Customer Analysis | 3 Consultants | 3 |  | 4 |  | 4 | 13 | 5 | 52 | 20 |  | total cost: |  | 1062000
Sales force analysis | 3 Consultants | 3 |  | 3 | 3 | 3 | 13 | 5 | 39 | 15
Process Analysis | 3 Consultants + 3 IT Specialists | 3 | 3 | 4 |  | 4 | 13 | 5 | 52 | 20
Data Analysis | 4 Consultants + 2 IT Specialists | 4 | 2 | 6 | 6 | 6 | 13 | 5 | 78 | 30
[5 empty] | 0 | 0 | 13 | 5 | 0 | 0
Target State Analysis |  |  |  |  | 0 | 0 | 13 | 5 | 0 | 0
Design Customer Relationship Strategy | 4 Consultants | 4 |  | 3 | 3 | 3 | 13 | 5 | 39 | 15
Prozess adaption | 3 Consultants + 1 IT Specialists | 3 | 1 | 4 |  | 4 | 13 | 5 | 52 | 20
Data model Creation | 4 Consultants + 2 IT Specialists | 4 | 2 | 3 | 3 | 3 | 13 | 5 | 39 | 15
Creation of Migrationconcept | 2 Consultants + 2 IT Specialists | 2 | 2 | 3 | 3 | 3 | 13 | 5 | 39 | 15
functional requirements | 13 Consultants | 13 |  | 5 | 5 | 5 | 13 | 5 | 65 | 25
Customizing | 5 IT Specialists |  | 5 | 7 | 7 | 7 | 13 | 5 | 91 | 35
Duaration of phase
|  |  |  | 60 | 30 | 60 | 260 | 100 | 780 | 300
Cost of ressource per day:
| Project manager |  |  | 1200
| Assistant |  |  | 600
| Consultants |  |  | 900
| IT Specialists |  |  | 900

## Phase 3
Execution
Project execution | Resources | count of it-specialists | count of consultants | days | workingdays it-specialists | workingdays consoltants | PM | Assistant
Development in India | 1 IT Specialist | 5 | 13 | 20 | 100 | 260 | 20 | 10 | Cost ofplanning:
Data Migration | 1 Consultants + 2 IT Specialists | 5 | 13 | 7 | 35 | 91 | 7 | 7 |  | Duration in days | Price per day | total cost
Pilot running | 5 Consultants + 2 IT Specialists | 5 | 13 | 5 | 25 | 65 | 5 |  | Project manager | 60 | 1200 | 72000
Implementation (testing environment) |  | 5 | 13 |  | 0 | 0 |  |  | Assistant | 30 | 600 | 18000
Testing |  | 5 | 13 |  | 0 | 0 |  |  | Consultants | 780 | 900 | 702000
Implementation (live system) | 3 IT Specialists | 5 | 13 | 12 | 60 | 156 | 12 | 6 | IT Specialists | 300 | 900 | 270000
Training | 3 Consultants | 5 | 13 | 13 | 65 | 169 | 13 | 6
Rollout of the CRM System | 8 Consultants + 2 It Specialist | 5 | 13 | 3 | 15 | 39 | 3 | 1
|  | 5 | 13 |  | 0 | 0
|  | 5 | 13 |  | 0 | 0 |  |  |  | total cost: |  | 1062000
|  |  |  | 60 | 300 | 780 | 60 | 30
60
| Project manager |  |  | 1200
| Assistant |  |  | 600
| Consultants |  |  | 900
| IT Specialists |  |  | 900

## Phase 4
Project closing | Resources | days | PM | Assistant | it-specialist | consultant | workingdays it | workingdays constultant
Approval | 1 IT Specialist | 5 | 5 | 5 | 5 | 13 | 25 | 65
Leassons learned | 1 Consultants + 2 IT Specialists | 15 | 15 | 15 | 5 | 13 | 75 | 195 | Cost ofplanning:
|  | 20 | 20 | 20 |  |  | 100 | 260 |  | Duration in days | Price per day | total cost
[9 empty] | Project manager | 20 | 1200 | 24000
[9 empty] | Assistant | 10 | 600 | 6000
[9 empty] | Consultants | 260 | 900 | 234000
[9 empty] | IT Specialists | 100 | 900 | 90000
[10 empty] | total cost: |  | 354000
Cost of ressource per day:
| Project manager |  | 1200
| Assistant |  | 600
| Consultants |  | 900
| IT Specialists |  | 900

## Zusammenfassung
Kosten
P1 | 60000
P2 | 1062000
P3 | 1062000
P4 | 354000
Gesamtkosten | 2538000